## College QIP 25-26
Quality Improvement Plan 2025/26
QIP No. | AFI | QIP Code: 1- 6 | Actions: | By Whom | Success Measures | By When | QIP Review 1 | RAG 1 | QIP Review 2 | RAG 2
1 | Although overall college achievement and retention have improved, outcomes for learners with EHCPs, High Needs (HN) and LDD remain below those of their peers and below national rates, indicating a need for stronger impact from current support and teaching strategies is required. Leads: Liz Burkey The Quality Team | 1 & 4 | Conduct targeted learning walks and Quality Review Activity (QRA) focused on EHCP, HN and LDD provision Conduct lesson visits in curriculum areas to review, adaptive TLA approaches such as scaffolding, independence strategies, communication approaches, and the use of support staff. Capture strengths and AFIs and feed these directly into departmental improvement plans. | APs, Heads of Area, Supported by the Quality Team | Evidence shows clear improvement in inclusive classroom practice with number of areas identified as areas of concern reduce between each SEND Review Board window 90%< of curriculum staff report improved staff confidence in supporting SEND learners, | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026
|  |  | Analyse outcomes, progress and provision quality for EHCP/HN/LDD learners Analyse attainment, retention, progress, attendance, and support‑plan compliance data at key checkpoints. (CQRPs, SEND Review Boards, QIP Reviews, for example) Produce risk reports (QSR Reports) for Head of Area highlighting areas requiring intervention. | SEND AP Heads of Area Supported by Quality Team | EHCP achievement should improve by 2% on 24/25 EHCP achievement for those outside of FIP to be above 80% HN achievement to improve by 1% compared to 24/25 be in line with those without HN HN achievement for those outside of FIP to be above 80% Cross college LDD (outside of FIP) to have 85%< acheivement LDD learners to continue to close the gap versus non-LDD with only <1% gap in 25/26 REDUCED ACHIEVEMENT GAP SEND/NON SEND. HN ACHIEVEMENT | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Predicted achievement is below that of those with no declared SEND / EHCP by 5% (SEND), 8.3% (EHCP) and 9.1% (HNF). Can we compare to 24/25 outcomes as this is our success measure.
|  |  | Ensure SEND learners belong at college and attend sessions well to give them the best chance of success and progression, whilst enjoying their time at college | SEND AP Heads of Area Supported by Quality Team | Reducing the attendance gap for SEND learners compared to the previous year (WHAT WAS 24.25) EHCP/HN/LDD learners all meet college KPI of 99% for feeling safe EHCP/HN/LDD learners all meet college KPI of 90% for positive overall experience | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | EHCP/HN/LDD attendance remains below that of their peers. SEND Review boards have focussed on this to look at any systematic issues. EHCP/HN learners are 2% below target for feeling safe. LDD learners are above the college KPI EHCP/HN/LDD learners exceed the repsonse outcome on being challenged to do their best - Review in line with measures in column F
|  |  | Review curriculum teams’ knowledge and understanding of support plans and inclusivity expectations Review a representative sample of support plans (e.g., EHCP outcomes, LSA guidance, individual profiles) against in‑class practice. Review the quality of teaching materials, SoLs and assessment plans to ensure inclusive practice is planned and sequenced throughout and meets the needs of the learners. | SEND AP Heads of SEND Supported by Quality Team | 90%< sample of support plans add value to the learners' studies and have effectively identified the support required. REMOVE Teachers demonstrate a clear score improvement with regards to delivering Quality First Teaching REMOVE 95%< of learners who receive support value it and it supports them to achieve and progress EHCP/HN/LDD learners rate the quality of teaching as good or better (90%<) | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | No progress on measuring impact yet - What has taken place? What are we doing if no progress has occurred? Have support plans (volume?) been sampled?
|  |  | Provide a targeted SEND CPD Programme Design a SEND focused CPD programme collaboratively with the SEND Team, Support and Quality Teams. This will include operational training and developing confidence in inclusive themes such as Quality First Teaching approaches, Trauma Informed, Equity in Education (EIE), Working with an LSA, for example. | SEND Team Student Support Team Quality Team | 90%< of curriculum staff value the support they receive from learning support department As a result of comprehensive SEND CPD, 95%< of learners who receive support value it EHCP/HN/LDD learners rate the quality of teaching as good or better (90%<) SEND CPD programme is designed and delivery method agreed for the 26/27 academic year | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Inclusion INSET Day delivered. SEND COG has been delivered and SEND Consultant has finalised SEND CPD programme for 26/27. What is the Plan? Outcome of INSET and COG?
|  |  | Implement a targetted approach to reducing the achievement gap in maths and English Prioritise in class support for maths and English classes with EHCP/HN learners in Deliver targetted 1:1 and small group interventions Review the timing of functional skills exams to maximise opportunities for success | SEND AP English & maths AP English & maths Team SEND Managers | Attendance in English and maths shows sustained improvement and narrows the gap with main programme attendance (>80 min and within 10% of MQ). English achievement for all SEND groups improves by 5%< Maths achievement for all SEND groups improves by 5%< | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | English and maths attendance is within 10% of main qual for HN & EHCP, but is not above 80% The majority of E&M classes have learning support in them
2 | Leaders and managers need to strengthen quality improvement activity to ensure all departments make sustained progress and meet the College’s ambitions. Rapid improvement is required in areas needing the most support, particularly English, maths, and Performing Arts. Leads: The Quality Team |  | Strengthen leadership oversight and accountability Implement a more robust cycle of QA activity (LWs, WRPs, QRA) with targeted frequency for those areas that are identified as Securing Improvement. Introduce monthly performance boards for all areas, chaired by Quality (AP/VP), to review progress, risks and required interventions as per Quality Handbook 2025/26) | VP Quality AP QA & QI TLAMS TLACs | Improvement in key performance indicators Achievement rates improve to meet or exceed College targets and national benchmarks year on year for Main Qualification (90%+), English and Maths (85%+) Attendance in English and maths shows sustained improvement and narrows the gap with main programme attendance (>80 min and within 10% of MQ). Retention 97%+ | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Quality Handbook processes in place from September and all procedures within it fully implemented. Monthly reviews ongoing as per the handbook windows. Predicted achievement for the end of year at college level is 89% +2% above last year. English attendance 80.62% variance to main qual -8.7%. Consistent for the last 3 quality status reports. Maths attendance 78.32%. Improving picture over the last 3x QSRs. Variance to main qual -11% Retention on target - 97.17% Withdrawal rate is currently 2.83% Current achievement projection being 88.5% (+1.5% on last year)
|  |  | Provide intensive support for underperforming curriculum areas Deploy TLAMs and the TLAC for coaching, joint planning and co-teaching. Implement short-term rapid improvement plans (Securing Improvement process) for at risk areas, with clear progression milestones. Increase the frequency of English and maths quality meetings, as outlined in the Quality Handbook, to strengthen data sharing and real-time intervention. | AP QA & QI TLAMS TLACs English & Maths Team | Evidence of stronger teaching, learning and assessment Learning walk and QRA outcomes show a reduction in “areas for improvement” and an increase in the positive strengths recorded and seen (LW dashboard and QRA Reports). Marked improvements in learner work quality (see WRP evidence), assessment compliance (100% PG1, 2 & 3 completion) and learners demonstrating improvement based on feedback recieved. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 431 learning walks undertaken to date. 67 Developmental Observations undertaken to date. Consistent theme on Learning Intentions, Impactful Activities and Checking Learning need to be developed further. 64% strengths identified in learning walks. 36% AFIs. 31 Work Review Panels undertaken across Term 1 & Term 2. 16 in Term 1, 15 in Term 2. Positive response to these from Heads of Area who have found them useful and the outcomes have supported them in designing strategies and approaches with their teams to improve on developemental feedback in particular. Markbook useage is still currently inconsistent for PG1 and PG2. This has been addressed in CQRP meetings. A program of staff development focussed on Live Modelling pedagogies is ongoing for all English and Maths staff from T2, in response to LW AFIs. Associated learning walks show some improvement in TLA. One maths lecturer is completely completing their QTLS qualification (MW from Quality as supporter) and another is due to start the L7 PGDip in Sep 2026. Three English lecturers are due to complete their ITE qualifications in summer 2026 and have received positive feedback on their observations; clear progress has been made throughout their two years on the course.
|  |  | Improve the quality of teaching, learning and assessment Deliver targeted CPD focused on areas of TLA bespoke to curriculum needs. For example: Behaviour for learning, Assessment for learning, Impactful feedback, Building rapport and culture with learners Ensure teachers in areas of most need undertake relevant professional development and peer observation cycles Use learner voice feedback to refine the curriculum offer and improve teaching approaches. | AP QA & QI TLAMS TLACs PD Team (Learner Voice) | Improved learner outcomes and experience Learner voice reports show year on year improvements in satisfaction for quality of teaching and learning (>90%). Learners demonstrate clearer articulation of skill development and progression when sampled, aligning with Future Skills expectations - PG1, 2 and 3 showing achievement at above target grade (>85% of learners achieving at or above target grade) X% of high grade achievement Achievement Rate >90% | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 6 week bespoke TLA programme for BUI/CON - details of programme can be provided on request. Individual action plans written and content of these supported by the AP-QA for BUI/CON. LWs and Dev Obs supported the TLA element of those individuals. Positive outcomes for those who have completed the informal process with evidence of improved TLA approaches and classroom management. 6 week bespoke TLA programme for HAC - details of programme can be provided on request. Started 09 March now full compliment of new staff have arrived in the department. Positive feedback from staff about the impact of the bespoke programme: "well planned", "excellent subjects", "really useful introduction." The team recommend specific staff with good practice to be peer reviewed by individuals to support areas for development. Formative Assessment & Feedback strategy is currently being delivered in Motor Vehicle. Specific 6 week focus with Engineering - LWs, quality drive A program of staff development focussed on Live Modelling pedagogies is ongoing for all English and Maths staff from T2, in response to LW AFIs. Associated learning walks show some improvement in TLA. Further CPD, individual coaching and monitoring activity will continue through T3 Two TLA Newsletters published to date. Themes - Building Community and Inspiring Excellence and Teaching That Sticks: Activities and Assessment for Lasting Learning Post Induction Learner Surveys: Adult 99.2% for teaching is good or better. 97.89% last year. EPYP - 86% teaching is good or better. -6% decline on last year. WBL - 80% teaching is good or better. -1.89% decline on last year. Predicted achievement for the end of year at college level is 89% +2% above last year.
|  |  | Strengthen the use of data to drive improvement Introduce Bi-weekly monitoring of attendance, progress, target grades and assessment completion, with automated risk flags to escalate concerns. Hold cross college data clinics (CQRPs) each term to evaluate progress and provide evidence-based support interventions Provide fortnightly Quality Status Reports to APs and HoA to review and action plan within curriculum. | VP Quality AP QA & QI | Effective and timely quality improvement processes Departmental QIPs show green RAG ratings by the final review cycle, demonstrating sustained and evidenced improvement. Curriculum review documentation shows strengthened self-assessment and accurate identification of AFIs. Securing Improvement outcomes show progress against identified areas for improvement - Progress RAG green on SI actions to justify SI no longer required | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | QSRs continue bi-weekly to provide data on a range of core KPIs and cross college monitoring of key objectives within curriculum, inclusion, PD, Apprenticeships, work experience, progress, destinations are elements reviewed in this process. 2/4 areas currently in Securing Improvement have shown considerable progress in their actions and discussions are underway as to whether they need to remain in SI moving forward. 1/4 areas has shown positive progress but will stay in SI due to the infancy of the staff across teaching staff and managers to provide an additional level of support for the rest of the academic year. Currently in the next wave of CQRPs.
|  |  | Enhance learner experience and progression outcomes Review and refine curriculum sequencing to ensure it supports accelerated progress, especially in English and maths resit programmes. Support managers to implement targeted attendance strategies (first-day calling, attendance contracts, parental engagement for 16–19s, flexible & varied delivery sessions). Review how curriculum embeds broader skills frameworks (e.g. Tutorial, STEPS & Future Skills) and provide coaching for improvements as aligned with college and sector priorities | VP Quality AP QA & QI APs, Heads of Area, English & Maths Team Supported by the Quality Team and the PD Team | Stronger cross college consistency 100% Initial Assessment completion for maths and English 100% Markbook completion - PG1, PG2, PG3 All departments demonstrate timely completion of QA processes with consistent quality of evidence. X% destination capture and X% positive progression to further studies, employment or training | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | IA completion - English 79.83% & Maths 81.61% Mid-year intended destinations: 83% positive progression to further study 17% to employment Markbook - 96% completion of set up. Completion of progress for PG1 and PG2 is varied and inconsistent. Quality process created to review SoLs to suport curriculum areas with sequencing of units / programmes. Too early in the process to provide findings.
3 | Leaders and managers need to ensure that learners across all areas can consistently evidence and articulate their skill development, including the behaviours and attitudes required for their chosen careers. The new ‘Future Skills’ framework should be implemented effectively in 2025/26 to strengthen learners’ understanding and ownership of their progression. Leads: Antonia Travers The Quality Team | 5 | Provide learners with high impact opportunities to develop their skills. Integrate the Future Skills framework into all curriculum planning and delivery Integrate the framework into Schemes of Learning, lesson planning, inductions, assessments and projects. Circulate clear, subject‑relevant exemplars for staff and learners to understand what high‑quality evidence of Future Skills looks like. Cross college services to provide an extended service which promotes skill development incluidng Student Engagament, Careers and Employibility, Academic Development. Maximise CEH partnerships to ensure learners have 4 or more employer engagamenets. | PD Team, Curriculum Teams, Supported by the Quality Team | Provide learners with high impact opportunities to develop their skills. 80% to demonstrate progress through target achievement All EPYP (exc FIP and ESOL) complete BFH Future Skills assessment with 80% showing progress in skill development 90% of learners to meet the minimum expectations for target completion (adjusted by learner type) Enrichment/careers participation increases by at least 15% from the previous academic year. 40% growth in trips in 25/26 in comparrison to 24/25 to develop and enhance wider skill development 80% Learners to recognise skill development following an academic development one to one or group session 80% of learners have 4 or more CEH Employer engagaments | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 34% of Future Skill Targets have been achieved at Feb 26. 3337 Future Skills targets recorded, 1123 achieved. An audit of tutorial targets recorded on ProMonitor identified that targets are generally not SMART, often lack sufficient detail, and are not consistently individualised to the learner. In response, college wide training on effective target setting is being planned, alongside the development of clear guidance and targeted action planning for each area audited to improve the quality and consistency of tutorial targets. 19.5% have reached CEH target (4 employer engagaments), which is to be expected at this point of the year. There is however positive impact and opportuntity for skill development evidenced in the college offer: - Engagement activity has increased by 157% at February 2026 in comparisson to February 2026. - Engagement trip participation has increased significantly, rising from 10 learners in the previous academic year to 123 learners this year, representing a 1,130% increase recorded through Navigate. including Comic Con (R2L: Communication, Prof: Networking, R2L: Organisation) and Rock Up (R2L: Communication, K2S: Resilience) - Careers Activities have increased 69% on Navigate from this time last year. - Careers meetings in 24/25 was 502 in total for whole year and 417 to date this academic year - 67% Learners recognised skill development following an academic development one to one or group session. The most frequently covered topics were 'Academic writing', 'Research and investigation', and 'Referencing', indicating a strong focus on core academic skills across sessions.
|  |  | Strengthen learners’ ability to articulate and demonstrate their behaviour and skill development Include Future Skills in induction along with ready to Ready to Learn, for example being Respectful links with communication and Empathy Strengthen reflective practice through structured learner logs, self‑assessment tools and regular guided reflection opportunities. Strengthen the use of consistent Future Skills language in lessons, tutorials and progress conversations. Support learners to practice and evidence their skill development at Work Expereince/Industry Placement Ensure all learners have tutorials where attendance, behaviours and skills are identified and discussed. | Curriculum Teams, Personal Tutors supported by the PD Team | Strengthen learners’ ability to articulate and demonstrate their behaviour and skill development >90% overall attendance for all college learners >92% of learners on First impression survey state they can confidently identify Ready to learn expectations and behaviours >90% of employers to rate learners attendance and punctuality as strong at end of placement >92% of employers rate learners having good ability to follow instructions and have positive presentation at end of placement 100% of learners show positive behaviours in course reviews >95% of learners can ariticutare their attendance Behaviour and attitude indicators (punctuality, readiness to learn, engagement) show a minimum 10% improvement college‑wide by year end. Across the college, ≥ 90% of learners demonstrate positive behaviour indicators in lesson observations (e.g., collaboration, independence). | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 89.04% collegiate attendance. 94.56% of learners stated they understood the READY to learn behaviours, attendance and punctuality expectations within the post induction survey. 81% of groups in course reviews could articulate their attendance. All groups could articulate READY behaviours. 93% of tutors record positive, professional behaviour in course reviews. 33 T level employers have recorded that 87% of learners show good personal presentation for the workplace, 228 total employers state 89% of learners have good time keeping and punctuality, as well as personal presentation and ability to follow instructions. 78% of employers feel their learners on WEX and T level placement are able to work independently
|  |  | Equip staff to implement the framework effectively Equip teachers with CPD focused on scaffolding skill development, coaching learners and recognising behaviours/attitudes in subject contexts. Equip teams with examples of strong practice from across the college to support consistent implementation. | PD Team, Heads of Area, Co-ordinators, Quality Team | Equip staff to implement the framework effectively Schemes of Learning, assessment plans and progress review documents all show clear mapping to Future Skills. Curriculum reviews show that teaching and learning routinely create opportunities to practise and evidence these skills. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | TLAM work within areas has identified areas for improvement with appraoches to sequencing and the quality of SoLs which is inconsistent. A SoL Audit / Review approach is currently being piloted with a view to it being rolled out in Term 3 with a focus on next year's planning and sequencing. Further scrutiny of this needs to be reviewed in term 3.
|  |  | Strengthen learner ownership of their progression Strengthen target‑setting and progress reviews so Future Skills are routinely discussed, recorded and revisited. Strengthen opportunities for learners to apply and showcase their skills through presentations, exhibitions, employer engagement and enrichment. All adult learners complete relevant and age-appropriate PD activities. Learners log their own activites and skill development on Navigate. | Curriculum Teams, Heads of Area, Co-ordinators, Personal Tutors, PD Team, Strategic Business Partnership Team | Strengthen learner ownership of their progression 100% of learners (16-19) evidence personal development on Navigate 100% of learners have positive destinations Enrichment/careers participation increases by at least 15% from the previous academic year. 90% of learners identify skill development through wider participation activity 80% of learners more knowledgable on progression route following Careers Activity 80% of learners are confident about their Progression following a careers one to one | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Target data in row 14 and requires imporvement. However 2,382 individual learners have skills recorded on Navigate. Across the dataset, skills are most frequently recorded in R2L Communication (8,333), K2S Critical Thinking (6,029), Professional Reflection (4,817), K2S Teamwork (4,068), K2S Resilience (4,031), R2L Empathy (3,949), CC Growith Mindset (3,381), R2L Organisation (3,087), Innovation Creativity (2,117), Professional Proactivity and adaptability (1,730), CC Social Action (1,631), Innovation Leadership (1,577), Professional Networking (1,508), Innovation Presentation (1,167), and CC Concious inclusion (933). 95% of 16-18 EPYP learners have a positive intended destination mid year 100% of learners record and identify skill development in wider participation 81.6% of learners are more knowledgable about progression routes following careers activity. 75% of learners were confident about their next steps following a careers one to one. The second and third BFH modules/assessments have not been developed.
4 | Leaders and managers should ensure that all adult learners, including those on evening provision, have access to a consistent, high-quality personal development curriculum and wider enrichment opportunities, aligning the offer more closely with that available to EPYP learners and apprentices. Leads: Antonia Travers Nick Phillips | 5 | Staff teaching adult provision to take ownership of the PD elements of their provision Delivery staff on adult-facing provision to meet with PD tutors and other relevant team members to ensure that every adult-facing course has suitable and age-appropriate PD activities built into its delivery plan. All adult learners who are following a programme in excess of 60 hours study across more than 12 weeks, complete relevant and age-appropriate PD activities linked to their identified barriers to success. | AP - Adult Heads of Adult Areas Adult Curriuculum Teams Supported by PD Team | 80% of all adult learners who have reported at least one barrier to success and who have engaged with the adult PD process report that they have made improvements in at least one measure by the end of their programme. 90% of adult learners on the survey state that they have developed wider skills and knowledge which will benefit them in their next steps following their course. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Cross-college adult provision group established with remit including review of all adult PD processes. Whole college mapping exercise undertaken with every area offering dedicated adult provision - results to follow.
|  |  | Enrichment offer for adults to be age-appropriate and available at times to suit adult learners Delivery teams to work within wider college systems to design and build an enrichment offer suitable for part time and evening adult learners leading to suitable, age-appropriate enrichment activities being available at a time and location to suit adult learners. PD Adult newsletter to be sent via Mailchimp which details a key PD topic a month | AP - Adult Heads of Adult Areas Adult Curriuculum Teams Supported by PD Team, Engagementt Team, Marketing, Careers Team, Strategic Business Partnership Team | Minimum 100 learners to attend. 90% positive learner voice on activities experienced. Adult PD Newsletter to be sent to 100% of adult learners who are active on programmes and who have identified that they are happy to receive materials from the college in this format, each month | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 8 adult reps/ambassadors New Student engagament manager is working on a refreshed model to allow adults to access enrichment e.g. online 122 adult learners have completed an enhanced CEIAG activity as a part of the programme. 4 adults due to win a Making a Difference Award at the student conference in March. New student Engagemet team are working with specific areas to plan adult activity.
|  |  | Student Experience activities are suitably promoted to adult learners Enrichment activities to be explained to adult learners during their IAG call, with this information being reinforced by delivery staff during learner induction sessions. Engagement team to share resources with staff (flyers) to show offer and update. Adult Newsletter to be sent termly with Engagement and careers updates along with PD. Careers to target adults with communications and personalised drop ins. Adult evening drop in evenings to be offered. Virtual careers evening drop in every month | AP - Adult Heads of Adult Areas Adult Curriuculum Teams Supported by PD Team, Engagement Team, Careers Team, Student Recruitment Team | All adult learners are aware of the enrichment opportunities available to them and how to access them A minimum of 100 apprentices and adults to engage with enrichmentactivities 75% click rate - adults PD Newsletter 1 apprentice to hold a position on the Student Union Leadership Team 100 Adult learners to engage in Careers activity 50 adult learners to engage with the Academic Development team | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Newsletter 1, entitled the Learning Loop, has been sent to adults however Mailchimp is not providing accurate click rates and is looking into this (not registering if email is opened on an Apple device). No adults in Student Leadership position. Newsletter 2 is due to go live next week. A Protected characteristics and FBV 15 minute short COD course is being designed on MS Forms to enable further personal development. 53 adult engagaments (one to ones and group information sessions) although the majority were from Counselling and Access
|  |  | College systems are reviewed, and if necessary revised to ensure that all adult PD and enrichment activities are being tracked in an appropriate manner Ensure that all delivery staff teaching adult-facing classes have full access to college systems including ProMonitor and Navigate and that they have received full training on how to use these systems. While current systems are being revised ensure that alternate recording systems are in place, robust and feeding into wider data collection. | AP - Adult Software Development Team Data Team PD Team | Adult PD sessions and enrichment engagement are being tracked on standard college systems Information from college systems is able to be used in a meaning full way during course reviews Future PD, enrichment and curriculum design in positively impacted by data from college tracking systems 1 | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | 13.8% of adults on Navigate 199 individual learners have recorded PD on Navigate (courses over 12 weeks). Adult managers will be reviewing Navigate over the next 3 weeks to upload Evidence. Survey is being reviewed to allow more PD/Enrichment data to be recorded and will be able to be reported on in QIP review 2.
5 | Leaders and managers need to improve achievement in Functional Skills Maths at all levels and in English at Level 2, while reversing the three-year decline in attendance. Attendance to English and maths lessons must be prioritised so that it rises to at least match attendance in main study programme qualifications and the current gap is reduced. Leads: Emma Hutchins The Quality Team | 3 | Implement a focused performance cycle for English & maths Implement monthly E&M performance boards to review attendance, in‑year achievement, at‑risk learners, and intervention. Align reviews to the English & maths Quality Meeting windows | AP Loxton Campus Heads of English & Maths English & Maths Team Supported by Quality Team | Increase achievement of high grades at GCSE by 10% in maths and English results for both November resits and Summer exams. Functional skills achievement to reach 80% by May half term | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | High grades have increased in English and Maths by 10% and 15% respectively in the November resit Functional skill achievement in on track with most learners now having sat an exam, all learners should have sat an exam by the end of Term (April 2nd)
|  |  | Prioritise attendance recovery with early‑warning triggers English and maths quality meetings to take place twice termly with HoA's and APs, these will focus on line by line data for learners not attending English and maths co-ordinators attend fortnightly at-risk meetings with campus officers and curriculum teams required to attend E&M at risk where needed. Review provision to ensure accessibility for all learners, include online and in person and 1-1 sessions where available E&M Heads to attend all SEND board reviews for each curriculum area | APs for each Campus Heads of English & Maths Heads of Area Curriculum Teams English & Maths Team Quality Team Welfare Team Admin Team | Attendance to steady at 80% for both maths and English and remain within 10% of main qual attendance | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | Attendance for English is steady at 80% and maths remains around 77-78% Areas not within the 10% of main qual attendance have targets in place to achieve this through the E&M quality meetings.
|  |  | Target TLA improvements where identified support is required Utilise the TLAMs and the TLAC, where necessary for coaching on TLA strategies, curriculum design and sequencing. Use Self and Peer Reviews as a vehicle to further support TLA development and reflection. Schedule and undertake regular learning walks which provide clear and achievable actions for development moving forward. Schedule and undertake Developmental Observations for any new staff not undertaking Teacher Training - L4 or L5. | AAP QA & QI TLAMS TLACs | Evidence of stronger teaching, learning and assessment Learning walk and QRA outcomes show a reduction in “areas for improvement” and an increase in the positive strengths recorded and seen (LW dashboard and QRA Reports). Marked improvements in learner work quality (see WRP evidence), assessment compliance and learners demonstrating improvement based on feedback recieved. Improved progress over time on formative milestones. 100% Self & Peer Reviews completed and demonstrating strong reflection ethos and teachign staff can articulate impact on their teaching practice. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026 | This remains a developing area. There has been a significant staffing challenge in the areas where not cancelling lessons has been prioritised over TLA quality at times. However learners are sitting exams and achieving but we need to push this rate up. Peer and self reviews have not taken place. A program of staff development focussed on Live Modelling pedagogies is ongoing for all English and Maths staff from T2, in response to LW AFIs. Associated learning walks show some initial improvement in TLA. Further CPD delivery, individual coaching and learning walk activity is scheduled to continue through T3 and into 2026/2027
6 | Leaders and managers should strengthen the performance of apprenticeship Standards that are not yet meeting the College’s expectations, particularly Business Administration and Manufacturing Engineer (Degree). Accelerating the apprentices progress is required to ensure timely and overall achievement rates that align with the strong performance seen across the College’s other apprenticeship programmes. Leads: Barney Willis Assistant Principals | 1 | Identify all standards that are 5% below college benchmarks in 24/25. Review historical withdrawal on programmes that are below college benchmarks and identify any themes or trends including, employers, time on programme at the point of withdrawal, assessors, learner & employer voice, attendance, key groups and destinations. Share this information with the apprenticeship managers and identify activities, such as increased assessor engagement, additional support, employer engagement and attendance strategies to produce a bespoke action plan for each apprenticeship Set success rate target based on current forecast for all identified standards. | AP Apprenticeship and Skills APs for each Campus Heads of Area Apprenticeship Managers Assessors Supported by Quality Team | 100% of all underpforming apprenticeship standards are identified and flagged to campus APs and Heads of areas All required data for withdrawals, duration, attendance, Learner and Employer voice, employer themes, assessors and SEND status is provided to apprenticeship managers within 4 weeks of identification. Each apprenticeship standard has additional improvement actions confirmed that each apprenticeship manager is responsible for. Success rates for timely and overall achievement are provided to all relevant apprenticeship managers within 4 weeks. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 31 Mar 2026
|  |  | Integrate increased management monitoring of the identified apprenticeship standards in the faculty apprenticeship performance management meetings to review attendance, forecasting of achievement overall, timely and for each key group and focus on these apprenticeship standard in the SEND Apprentice Progress meetings to enable a reduction in any gaps. Set timely and overall targets for the faculty to meet. Review Smart Assessor and Apprenticeship Management dashboard date to identify apprentices at risk and track and monitor progress and achievement. | AP Apprenticeship and Skills APs for each Campus Heads of Area Apprenticeship Managers Assessors Supported by Quality Team | Each apprenticeship faculty meeting agenda and minutes confirm review of identified standards, the identified data and any actions as a result of the review. All dashboard data to be logged at each meeting to show increase/decrease over time. Each standard to achieve the set achievement target. Minutes show current forecast against target set | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026
|  |  | Apprenticeship managers to monitor Smart Assessor progress for the identified apprenticeship standards and include in 1:2:1s with assessors setting targets and actions to ensure improvement for all apprentice groups on the specific standards. Ensure all CDPs are up to date and are in use, using the most recent template and including all madatory elements. Check Smart Assessor e-portfolios are set up correctly and include the relevant employer manager ensuring they have access to their apprentice's portfolio. Review STEPS to check and confirm apprentices are progressing and developing areas outside of the qualification. Review PD dashboard for these standards to check effectiveness. | AP Apprenticeship and Skills APs for each Campus Heads of Area Apprenticeship Managers Assessors Supported by Quality Team and the PD Team | All Apprenticeship managers 1:2:1 records show evidence review against target for each assessor. Where actions are set, there is evidence of a positive impact or corrective action implemented. CDP audits show 100% of all apprentices on poor performing standards have a fully complete CDP that has been shared with the employer and apprentice through the progress review process 100% of all employers have been added to Smart Assessor and can review apprentice's progress. STEPS dashboard for every identified standard shows 100% of apprentices are achieveing the mandatory requirements | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026
|  |  | Use the Progress Review and CDP audit process to identify specific areas of poor or good practice. Implement staff CPD to address these for any staff delivering on the poor performing standards. Use preformance management where CPD is implemented for staff that show no improvement and where no mitigating circumstances are identified. Monitor scores over time to check that compliance and quality is rapidly improving | AP Apprenticeship and Skills APs for each Campus Heads of Area Apprenticeship Managers Assessors Supported by Quality Team | Progress review and CDP audits are completed monthly with the results added to the faculty overview spreadsheet Results of all Progress Review and CDP audits are shared monthly and show an improvement in quality and compliance for each assessor assessing on the identified standards. Where this is not evident, all staff are given individualised CPD All staff who require CDP actively undertake and complete all activities identified. | Monitor: QIP Review 1 Monitor: QIP Review 2 Monitor: QIP Review 3 Deadline: 26 June 2026
QIP code:
1 |  | College Core Priorities
| Increase the amount of academic progress learners and apprentices make based on their individual starting point with a focus on: |  |  |  | Q - are these core priorities now defunct?
| a) Ambition and expectations of learners and apprentices. |  |  |  | Q: Do we need the other tabs?
b) The level of challenge in lessons.
c) Academia & Research
2 | d) High quality feedback (and feedforward).
3 | Further develop the maths and English skills of all learners and apprentices.
4 | Ensure the SEND Framework permeates the organisation and that TLA is inclusive for all.
5 | Ensure that all learners, especially adults and apprentices benefit from a high-quality Personal Development curriculum and programme.
6 | Effectively develop the Digital and Technological skills and knowledge learners and apprentices need to be successful in the future (including the use of AI)
Other

## College wide CPD
HT/Quarter | Dates: | QIP Priority | Delivery staff: | INSET/CPD / Teach meet activity | IMPACT on TLA
1
2
3
4

## Individual Staff CPD
Staff name: | CPD or COG 23/24 | CPD or COG 24/25 | CPD 25/26 | How will expertise be share within curriculum team or beyond?
DO WE NEED THIS FOR COLLEGE WIDE QIP?
DO WE ADD THIS AS SECTION?AREA specific CPD?

## ISO
WCGQUAL-246866681-24004
INTERNAL